Derry City and Strabane District PEACEPLUS Partnership Board

Meeting Date: 	Tuesday 15th October 2024

Time: 			10.00am – 11.30am

Venue:			Glenelly Room, DCSD Council Offices, Strabane.

AGENDA ITEM

1. Meeting Opening

1.1 Welcome and Apologies

1.2 Conflict of Interest

Appendix D Notes standing conflicts of interest. All members please check, especially anyone relatively new to the Board. Pass any updates to Fiona.

1.3 Minutes of previous meeting / Matters arising (p.6-11)

Recommendation: Review minutes for any changes and/or actions and adopt.

2. Update from PEACE Team (Sue)

2.1 Update on SEUPB

LOO received: Council has a full Letter of Offer for £8,047,327 (€9,254,427). Possibly the only NI council to have letter in sterling – others are reporting being turned down despite business cases.

Lump Sum: Received 23rd Sept. Issued in Euros ie. Not converted at agreed SEUPB working rate. Should have been €100K @ 1.15 planning rate. i.e.   £86.950 instead we received 81,987.37. Difference of £4,962.63.

Request for Advance: submitted with required business case 23rd Sept. £1,609,446 (20%). Ciarán Hanna confirmed receipt on 24/9/24 and indicated Emma Shields would be working on this.

Staff training: Scheduled half-day training 22nd October in Dungannon by SEUPB. No Q&A.

2.2 General update on PEACE Team work

PEACE IV: Now officially closed.

PEACEPLUS Procurement: A total of 36/58 projects are now in delivery stage. The remaining 22 projects are either currently live as tenders or are presented to October Board. With the exception of any potential repeat tenders from non-submissions etc. the procurement phase is ahead of schedule and the programme should be mainly contracted in 2024.

September: Ran final (?) Tender Training: 2pm 3rd September St.Columb’s Park House. Ran two initial Mandatory Training for Projects: Mon 23rd am Strabane or Tue 24th am St.CPH. Designed and built online interim evaluation and monitoring systems.

October and November: Will be busy with large volume of tender assessments. Potential for up to 14 to be ratified at November committee and go through contracting in December. A further 6 tenders likely to be advertised.

December and January: Focus will be on assessment of remaining tenders and taking all through standstill, pre-contract checks and finalizing contracts.

3. Confidential Update on Tender Assessments. (Detail at meeting only) – PEACE Team

3.1 Non-confidential (processes fully completed since last Board Meeting)

Key information included in Traffic Lights. Fuller paper to be presented at the meeting.

| Tender Ref: | Tender Title: | Committee |
| --- | --- | --- |
| T24-043BUS | PEACEPLUS Cricket Connects | July |
| T24-060BUS | PEACEPLUS F.Y.I. (Foyleside Youth Initiative) | July |
| T24-063BUS | PEACEPLUS Rural Teens | July |
| T24-061BUS | PEACEPLUS Theme 1.1 Be Wild | July |
| T24-062BUS | PEACEPLUS Theme 1.1 Sperrin Youth Voices | July |
| T24-064BUS | PEACEPLUS Theme 1.1 Let’s Talk (Youth) | July |
| T24-086BUS | PEACEPLUS Empowered Communities Strabane Reissue | August (delegated authority + Sept) |
| T24-093BUS | PEACEPLUS Connect Project (BAME) | August (delegated authority + Sept) |
| T24-059BUS | PEACEPLUS IDEA Project | Not-appointed |
| T24-065BUS | PEACEPLUS Theme 1.1 Our Journey to Peace | No tenders received |
| T24-045BUS | PEACEPLUS Theme 1.1 Out and About (BAME) | No tenders received |

3.2 Confidential (October Committee)

Update on what has been sent to committee for approval. If any conflicts of interest with organisations which tendered for the following, Board members need to leave the room:

| Tender Ref: | Tender Title: | Committee |
| --- | --- | --- |
| T24-109BUS | ## PEACEPLUS IDEA Project | October |
| T24-089BUS | ## PEACEPLUS War and Peace Project | October |
| T24-110BUS | ## PEACEPLUS Out and About (BAME) | October |

3.3 Currently live and/or recently closed and due to be assessed

| Theme | Tender | Issued | Closing date |
| --- | --- | --- | --- |
| CRT | T24-120BUS PEACEPLUS Street Art Reimaging | Fri 13th Sept | 18th October |
| CRT | T24-152BUS PEACEPLUS Urban Social Farm (Reissue) | Fri 6th Sept | 11th October |
| CRT | T24-155BUS PEACEPLUS Unlocking Silent Heritage (Reissue) | Fri 6th Sept | 11th October |
| TPC | T24-123BUS PEACEPLUS Arts & Collaborative Resilience | Fri 6th Sept | 11th October |
| TPC | T24-126BUS PEACEPLUS Reimage-Recycle | Fri 6th Sept | 11th October |
| TPC | T24-128BUS PEACEPLUS Art: Recovery to Discovery | Fri 6th Sept | 11th October |
| TPC | T24-124BUS PEACEPLUS Ballyarnett Early Years Project | Fri 6th Sept | 11th October |
| TPC | T24-122BUS PEACEPLUS Be Driven | Fri 6th Sept | 11th October |
| TPC | T24-121BUS PEACEPLUS Ballyarnett Women's Programme | Fri 6th Sept | 11th October |
| TPC | T24-125BUS PEACEPLUS Ballyarnett Men's Programme | Fri 20th Sept | 25th October |
| CCD | T24-130BUS PEACEPLUS Our Present Past | Fri 13th Sept | 18th October |
| CCD | T24-132BUS PEACEPLUS Distance Travelled | Fri 13th Sept | 18th October |
| CCD | T24-131BUS PEACEPLUS Forward Thinking | Fri 13th Sept | 18th October |
| CCD | T24-129BUS PEACEPLUS Fit for Purpose (Soccer) | Fri 13th Sept | 18th October |
| CCD | T24-135BUS PEACEPLUS Cecil Frances Alexander Celebrated | Fri 13th Sept | 18th October |
| CCD | T24-134BUS PEACEPLUS The Exodus Project | Fri 13th Sept | 18th October |

Recommendation: That the Board should note the outcomes of the assessment panels and the decisions sent to council for ratification. That any tenders not awarded should be readvertised.

3.4 New draft tender specifications for presentation to the Board.

Update on 6 tenders. Details not circulated in advance – presented at meeting. If any conflicts of interest, Board members need to leave the room:

| Theme | Tender | Lead MC/FL |
| --- | --- | --- |
| TPC | T24-127BUS PEACEPLUS A Centre of Hope | FL |
| CCD | T24-133BUS PEACEPLUS Our Shared History (Political Ex-Prisoners) | FL |
| CCD | T24-136BUS PEACEPLUS LGBTQIA+ Awareness | MC |
| CCD | T24-137BUS PEACEPLUS Victims/Survivors Social Programme | MC |
| CCD | T24-138BUS PEACEPLUS Culture Club | FL |
| CCD | T24-163BUS PEACEPLUS Journey to Peace Reissue | SD |

Recommendation: That the Board consider each tender specification, comment/amend if required and approve for public advertisement.

4. CRT (Comm Regen & Transformation)/ Management / Comms Update

4.1 Update from Steering Group Meeting - Chair Gerard Deane

Held 10th September @ Newgate Cultural Centre.

Management workplan – Steering Group discussed updates/issues on Lump Sum, Advance process, CPD, Evaluation and Monitoring (and associated risks from systems not in place from SEUPB), Auditing/First Control Function (and associated risks/impacts for financial planning from systems not in place until Mid-Nov from SEUPB – update that we will be appointed off a list so no secondary procurement required.) UK legislation impact on tendering (date now deferred until February 25). Welcomed Connor as the new trainee administrator in team.

Communications Workplan – Noted the tender training and the mandatory training for projects being delivered in September. Poster available for groups. Press coverage of launch and various project launches. Draft press release template issued to groups. Website updated July. E-bulletin issued summer and September.

CRT Workplan – Scrutinised and approved draft specification T24-120BUS Street Art Reimaging for issue.

4.2 CRT workplan update (PEACE Team)

Management Workplan: Brief Overview of interim Evaluation and Monitoring system.

CRT Workplan: See traffic lights for updates on CRT Workplan implementation. PEACE Team can answer any queries on specifics if required.

Communications workplan: Further e-zines to be issued in Autumn. Next magazine may wait until programme is fully contracted in early 2025.

5. TPC (Thriving Peaceful Communities Theme) Update

5.1 Update from Steering Group Meeting - Chair Alison Wallace

Meeting held 4th September in Strabane. Steering group received a post-summer update of the work which had happened and some key concerns. Key focus was then on tender scrutiny and approval (with some minor alterations) of 7 tenders. T24-123BUS PEACEPLUS Arts and Collaborative Resilience; T24-126BUS PEACEPLUS Reimage-Recycle; T24-128BUS PEACEPLUS Art: Recovery to Discovery; T24-124BUS PEACEPLUS Ballyarnett Early Year’s Project; T24-122BUS PEACEPLUS Be Driven; T24-121BUS PEACEPLUS Ballyarnett Women’s Programme; T24-125BUS PEACEPLUS Ballyarnett Men’s Programme.

5.2 TPC Workplan Update (PEACE Team / Mary Claire / Fiona)

See traffic lights for updates on TPC Workplan implementation. PEACE Team can answer any queries on specifics if required.

6. CCD (Celebrating Cultural Diversity Theme)

6.1 Update from Steering Group Meeting - Chair Sharon Doherty

Meeting held in Irish Street Community Centre on 12th September. Steering group received a post-summer update of the work which had happened and some key concerns. Discussion around the Journey to Peace tender which has been issued twice with no submissions and sensitivities in wider context. Approval from the Steering Group to put minor change request to SEUPB to widen cross-interface and cross-community to cross-interface and/or cross-community. Key focus was then on tender scrutiny and approval (with some minor alterations) of 6 tenders. T24-130BUS Our Present Past; T24-132BUS Distance Travelled; T24-131BUS Forward Thinking; T24-129BUS PEACEPLUS Fit for Purpose (Soccer); T24-135BUS PEACEPLUS Cecil Frances Alexander Celebrated; T24-134BUS PEACEPLUS The Exodus Project.

6.2 CCD Workplan Update (PEACE Team / Mary Claire / Fiona)

See traffic lights for updates on CCD Workplan implementation. PEACE Team can answer any queries on specifics if required.

7. Meeting Closing

7.1 AOB

7.2 Date of Next Meetings (see appendix as well):

Board: 10am 10th December 24 @ Strabane DCSDC Glenelly Suite (Strabane)

CRT: 10am 12th November 24 @ Strabane. Aodhán Harkin offered to host. Venue TBC

TPC: 10am 6th November 24 @ Strabane DCSDC Glenelly Suite (Strabane)

CCD: 10am 14th November 24 @ Shared Future Centre (Waterside)

Derry City and Strabane District PEACEPLUS Partnership Board

Minutes of Meeting

Meeting Date: 	Tuesday 11 June 2024

Time: 			10.00am – 11.15am

Venue:			Holywell Trust

| Sue Divin | DCSDC | Chelsea Cooke | DUP |
| --- | --- | --- | --- |
| Gemma Scarlet | DCSDC | Catherine Cooke | FWIN |
| Mary Claire Kerlin | DCSDC | Mary O’Neill | NI Housing Executive |
| Fiona Lafferty | DCSDC | Ursula Doherty | Strabane LGP |
| Kevin O Connor | DCSDC | Nikki Yau | FREF |
| Marie Gallaher | Dept of Communities | Sharon Doherty | St Columbs PK Rec Trust |
| Deborah Cross | EA | Charles Lamberton | Moor LGP |
| Lisa Moore-Maguire | Foyleside LGP | Martin Duffy | Derg LGP |
| *Noelle Donnell | Hummingbird (NI) CIC (online) | Aisling Hutton | SF |
| Derek Moore | NW Cultural P’Ship | Alison Wallace | Waterside LGP |
| Cat Brogan | BBI | Claire Russell | Sperrin LGP |
| Grace Ui Niallais | SF | Darren Guy | UUP |
| *Gus Hastings | Faughan LGP (online) |  |  |

*Members who attended online

- Meeting Opening

  - Welcome and Apologies

Apologies received from Christopher Jackson, Aodhan Harkin, Ciaran McLaughlin DAERA.

  - Conflict of Interest –

Note appendix D now in place as standing conflicts of interest. Members to update with Fiona.

  - Minutes of Previous meeting/Matters arising - Board meeting of Tuesday 12th March 2024 were held to be an accurate record.

Proposed:  Catherine Cooke  		                Seconded:  Derek Moore

2. Update from PEACE Team (Sue)

2.1 Progress of Bid / Update on SEUPB

Sue updated members on PEACEPLUS Bid with SEUPB.   An email received on 21st March 2024 from SEUPB email confirming that the Local Co-designed Action Plan has been fully funded.   A further email on the 16th April 2024 from SEUPB issuing a conditional approval letter with standard pre-commencement conditions before the issue of LOO.

Preconditions update: SEUPB have confirmed they now have all required info from us to complete capacity checks. State Aid assessment has been completed and returned. Double Funding declaration signed and returned. Case Officer is Ciaran Hanna. He will be working to complete aspects at SEUPB end before LOO will be issued. ETC 22(4h) Declaration Form also completed.

2.2 Update on PEACE Team work

Sue updated members that the closure is still pending on PEACEIV programme but nothing outstanding from DCSDC end.

Next key phase will involve issuing of letters of tender outcomes and the 10-day standstills letters followed by issuing Letters of Offer (subject to pre-contract checks).  Overall, 2 SLA’s and 19 tendered projects are good to proceed once DCSDC LOO in place. A further 7 after June Committee. Potentially 9 further after July Committee. Total: 37/58. There are 2 re-tenders to be re-issued in due course, but apart from those there will be a pause in any further new tenders being issued until the Autumn. Procurement is on track with schedule and the break is needed to allow staff to get those 37 projects up and running.

3. Confidential update on Tender Assessments.

3.1 Recent tender outcomes update

Confidential Update on Tender Assessments.  (Papers at meeting only) – PEACE Team

Derek More, Martin Duffy, Ursla Doherty and Grace Uí Niallais left the room before papers were circulated.

Sue informed members that all the tenders listed below for the May committee can be awarded. Others are currently going through June committee.

| Tender Ref: | Tender Title: | Committee |
| --- | --- | --- |
| T24-039BUS | PEACEPLUS Theme 1.1 HumanKind; | May |
| T23-139BUS | PEACEPLUS Theme 1.1 Culmore Connections; | May |
| T23-140BUS | PEACEPLUS Theme 1.1 Culture Now Showcase; | May |
| T23-137BUS | PEACEPLUS Theme 1.1 Pre-Teen Transition Project; | May |
| T24-017BUS | PEACEPLUS Theme 1.1 Columba Journey; | May |
| T23-138BUS | PEACEPLUS Theme 1.1 Create: Youth Digital and Music Project; | May |
| T23-136BUS | PEACEPLUS Theme 1.1 Our Space Our Place. | May |
| T24-071BUS | PEACEPLUS Theme 1.1 Food Poverty Project | June |
| T24-074BUS | PEACEPLUS Theme 1.1 Derg Future Festivals | June |
| T24-047BUS | PEACEPLUS Theme 1.1 Muintearas (Belonging) | June |
| T24-014BUS | PEACEPLUS Theme 1.1 Creating Creatives | June |
| T24-015BUS | PEACEPLUS Theme 1.1 Strabane Youth Programme | June |
| T24-016BUS | PEACEPLUS Theme 1.1 Our Place, Our Planet | June |
| T24-044BUS | PEACEPLUS Theme 1.1 Farming and Environmental Champions | June |

The successful applicant for the Creating Creatives tender withdrew as they were closing down and it was awarded to the second placed applicant Maywe.

3.2 Other general tender updates

Current Live tenders:

Deadline 7th June 12 noon:

T24-043BUS PEACEPLUS Cricket Connects

T24-060BUS PEACEPLUS F.Y.I. (Foyleside Youth Initiative)

T24-059BUS PEACEPLUS IDEA Project

T24-063BUS PEACEPLUS Rural Teens

Deadline 14th June 12 noon:

T24-061BUS PEACEPLUS Theme 1.1 Be Wild

T24-062BUS PEACEPLUS Theme 1.1 Sperrin Youth Voices

T24-064BUS PEACEPLUS Theme 1.1 Let’s Talk (Youth)

T24-065BUS PEACEPLUS Theme 1.1 Our Journey to Peace

T24-045BUS PEACEPLUS Theme 1.1 Out and About (BAME)

2 reissues deadline 5th July 12 noon:

T24-086BUS PEACEPLUS Empowered Communities Strabane Reissue

T24-093BUS PEACEPLUS Connect Project (BAME)

Decision: The Board noted the outcomes of the assessment panels and the decisions sent to council for ratification. Any tenders not awarded should be re-advertised.

4.0 CRT (Comm Regen & Transformation) Management / Comms Update

4.1 Update from Steering Group Meeting - Chair Gerard Deane

The CRT meeting was held on 14th May @ Newgate Cultural Centre.   No elected reps present.  Members were informed that the PEACE Team was getting an intern Connor Crawford and that they would have chance to meet him after the summer.  Charles Lamberton and Chelse Cooke wanted their apologies recorded for the CRT meeting – this was noted.

Sue then referred members to the traffic lights for updates on CRT Workplan implementation and the two new contracts for consideration (Papers/Discussion at meeting only).  No Conflicts of Interest recorded.

T24-089BUS PEACEPLUS War and Peace (Mary Claire)

T24-090BUS PEACEPLUS Unlocking Our Silent Heritage (Fiona)

Alison emphasized engaging district wide urban and rural.  Catherine mentioned a public launch for the projects and that the wider communities would be part of the co-design process.  Officers agreed to feed back to the team in charge of delivering the projects.  Members were informed that these tenders fall under the Service Level Agreements of two DCSDC led projects. PEACE Team will however co-ordinate the procurement of these tenders and the timing of procurement will be agreed with the DCSDC project steering groups in Environment/Regeneration/Museums services.

Recommendation:  Officers to feed back to the Environment/Regeneration/Museum teams to engage district wide urban and rural communities.

## 4.2 Management Workplan – any new updates (Sue and Gemma)

Sue introduced Gemma to board members and details of her Finance and Monitoring Role within the PEACEPLUS Team.  Following an update with Ciera Kane Evaluation & Monitoring lead on 21 May 2024 and TEO, Gemma is to develop up monitoring and evaluation forms and reporting templates that track participants as SEUPB do not have this system developed yet.  Members were also made aware of the concerns the team had around the Financial Controller.  As of yet SEUPB has not developed up a call off list of auditors which they will assign to each Local Plan and it is not clear how much the costs for the Auditor will be for the entirety of the programme.

Members were informed that Mandatory half-day training for all contracted projects needs designed and rolled out in the coming months.  This is more likely to be scheduled around September time and it will cover procurement, communications, evaluation and monitoring. Also establishes open communication and trust between projects and PEACE Team.

Decision:  Members decided to put key concerns into writing and actioned a letter on behalf of the board to be sent detailing their concerns around Monitoring and Evaluation and the appointment of the Auditor and if they could provide a timeframe when these would be in place. Updates were also required from SEUPB on progress with closing PEACEIV and a number of other issues.

4.3 Communications Workplan –  Sue updated members on the following:

- April & May e-bulletins issued.

- Marketing materials – Notebooks & Stickit labels procured. Further banner stands.

- Feedback from Launch event and coverage.

- Poster for projects designed and procured – sent to printer. Will issue to all projects.

- Probably aim to develop a new magazine in Autumn 2024.

5. TPC (Thriving Peaceful Communities Theme) Update

5.1 Update from Steering Group Meeting - Chair Alison Wallace

A meeting was held Wednesday 1st May in Strabane. Quorate. Group discussed and approved 6 new tenders each with minor or no changes: T24-043BUS PEACEPLUS Cricket, T24-059BUS PEACEPLUS IDEA (Intergenerational Dialogue Engaging Arts), T24-060BUS PEACEPLUS F.Y.I (Foyleside Youth Initiative), T24-061BUS PEACEPLUS Be Wild, T24-062BUS PEACEPLUS Sperrin Youth Voices, T24-063BUS PEACEPLUS Rural Teens. Also discussed and noted concerns around the potential change from SEUPB on the Financial Controller role as budgets in the individual projects are quite tight in many instances.

5.2 TPC Workplan Update (PEACE Team / Mary Claire / Fiona)

Fiona and Mary Claire updated members on TPC workplan implementation.   Empowered Communities Strabane has had to be reissued, otherwise theme is on track. Significant numbers of tenders currently live.  No issues raised.

6. CCD (Celebrating Cultural Diversity Theme)

6.1 Update from Steering Group Meeting - Chair Sharon Doherty

Meeting held Thursday 9th May @ Shared Future Centre. (Quorate)  The tender specifications for 2 tenders were considered: T24-064BUS PEACEPLUS Theme 1.1 Let’s Talk (Youth) and T24-065BUS PEACEPLUS Theme 1.1 Our Journey to Peace. These were approved and now been advertised. As per other steering groups, noting concern over the lack of clarity from SEUPB on the financial controller (internal) role.

All 3 tenders approved by the steering group to proceed to procurement. These are now advertised and in the public domain.

6.2 CCD Workplan Update (PEACE Team / Mary Claire / Fiona)

Fiona and Mary Claire took members through the CCD Workplan implementation.   Connect (BAME) Project has had to be re-advertised, otherwise theme is currently on track.  No issues raised.

7. Meeting Closing

7.1 AOB

7.2 Date of Next Meetings (see appendix as well):

There are no scheduled meetings in July/August. If any emergency issues come up, team will go through Chair and Co-Chair in first instance to make decisions.

Board: 10am 8th October 24 @ Strabane DCSDC Glenelly Suite (Strabane)

CRT: 10am 10th September 24 @ New Gate Arts & Cultural Centre (Fountain)

TPC: 10am 4th September 24 @ Strabane DCSDC Glenelly Suite (Strabane)

CCD: 10am 12th September 24 @ Shared Future Centre (Waterside)

Appendix A: Board Member’s Attendance 2023/24

| Statutory Pillar |  | 9/23 | 11/23 | 1/24 | 3/24 | 6/24 | 10/24 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| William Calderwood (d. Shannagh Farren) | PSNI |  | x |  |  |  |  |
| Deborah Cross (d. Declan Gallagher) | EA |  | x |  |  | x |  |
| Marie Gallaher (d. Sharon McCullagh) | DfC |  | x |  | x | x |  |
| Mary O'Neill (d.Noel McNulty) | NIHE | x |  | x | x | x |  |
| Seamus Ward (d.Bronach McMonagle) | WHSCNI | x |  | x | x |  |  |
| Ciaran McLaughlin (d. Gerard O’Neill) | DAERA |  |  | x | x |  |  |
| Social Partners – Local Growth Partnerships |  |  |  |  |  |  |  |
| Jacki Connolly (d.Darren Kirby) | Ballyarnett | x | x | x | x |  |  |
| Martin Duffy (d. Andy McKane) | Derg | x |  | x | x | x |  |
| Aodhán Harkin (d.Ursula Doherty) | Strabane | x | x | x |  | x |  |
| Gus Hastings (d.Martin McCartney) | Faughan | x | x | x |  | x |  |
| Charles Lamberton (d.Seamus Breslin) | Moor |  |  | x |  | x |  |
| Claire Russell (d.Patricia McNulty) | Sperrin | x | x | x | x | x |  |
| Alison Wallace (d.Geraldine Doherty) | Waterside | x |  | x |  | x |  |
| Lisa Moore-Maguire (d. Jim McColgan) | Foyleside | x | x | x | x | x |  |
| Elected Representatives Pillar |  |  |  |  |  |  |  |
| Aisling Hutton | SF |  |  |  | x | x |  |
| Ruairi McHugh | SF |  | x | x | x |  |  |
| Brian Harte | SF |  |  |  | x |  |  |
| Christopher Jackson | SF | x | x | x | x |  |  |
| Patricia Logue | SF | N/A | N/A | N/A | N/A |  |  |
| Grace Uí Niallais | SF | x |  | x | x | x |  |
| Martin Reilly | SDLP |  |  | x |  |  |  |
| Declan Norris | SDLP |  | x | x |  |  |  |
| Brian Tierney | SDLP |  | x | x |  |  |  |
| Chelsea Cooke | DUP | x | x | x | x | x |  |
| Darren Guy | UUP | x | x |  |  | x |  |
| Paul Gallagher | IND | N/A | N/A | N/A | N/A |  |  |
| Social Partners Pillar |  |  |  |  |  |  |  |
| Gerard Deane (d. Fiona Corvan) | Holywell | x | x | x | x |  |  |
| Catherine Cooke (d. Bethany Moore) | FWIN | x | x | x | x | x |  |
| Sharon Doherty (d. Michelle Simpson) | St.CPH |  | x | x | x | x |  |
| Noelle Donnell (d. Sinead Barr) | H’bird |  | x | x | x | x |  |
| Dominic Bonner (d. TBC) | YANI | x |  |  | x |  |  |
| Derek Moore (d. Kyle Thompson) | NWCP | x | x | x | x | x |  |
| Kyra Reynolds (d. Cat Brogan) | BBI | x | x | x |  | x |  |
| Nikki Yau (d. Agnieszka Luczak) | FREF | x | x | x | x | x |  |

Appendix B: PEACEPLUS Timetable of meetings for Board & Steering Groups

|  | Sept 24 | Oct 24 | Nov 24 | Dec 24 | Jan 25 | Feb 25 | Mar 25 | Apr 25 | May 25 | Jun 25 | Jul 25 | Aug 25 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| PEACEPLUS Board (Wk 2 Tuesdays) |  | 8th |  | 10th |  | 11th |  | 8th |  | 10th | - | - |
| CRT (Cityside Wk 2 Tuesdays.) | 10th |  | 12th |  | 14th |  | 11th |  | 13th |  | - | - |
| TPC (Strabane Wk 1 Wednesdays Glenelly or Function Rm, Strabane DCSDC Office) | 4th |  | 6th |  | 8th |  | 5th |  | 7th |  | - | - |
| CCD (Waterside Wk 2 Thursdays. Shared Future Centre) | 12th |  | 14th |  | 16th |  | 13th |  | 15th |  | - | - |

** No Board or Steering Group Meetings July or August (except exceptional circumstances)

Appendix C – Membership of PEACEPLUS Steering Groups

| CRT Community Regeneration & Transformation, Management and Communications. | TPC Thriving and Peaceful Communities. | BRCI Celebrating Cultural Diversity. |
| --- | --- | --- |
| Venue: Cityside | Venue: Strabane | Venue: Waterside |
| Day/Time/Week: Tue am Week 2 of month | Day/Time/Week: Wed am Week 1 of month | Day/Time/Week: Thurs am Week 2 of month |
| 1 Ciaran McLaughlin (DAERA) | 1 Marie Gallaher (DfC) | 1 Deborah Cross (EA) |
| 2 Mary O’Neill (NIHE) | 2 William Calderwood (PSNI) | 2 Seamus Ward (WHSCNI) |
| 3 Gerard Deane (Holywell) | 3 Noelle Donnell (Hummingbird) | 3 Catherine Cooke (FWIN) |
| 4 Kyra Reynolds (BBI) | 4 Anne McTaggart (YouthAction NI) | 4 Sharon Doherty (St.Columb’s Pk House) |
| 5 Derek Moore (NWCP) | 5 Alison Wallace (Waterside DEA) | 5 Nikki Yau (Migrant Centre NI) |
| 6 Charles Lamberton (Moor DEA) | 6 Lisa Moore-Maguire (Foyleside DEA) | 6 Martin Duffy (Castlederg DEA) |
| 7 Aodhán Harkin (Strabane DEA) | 7 Gus Hastings (Faughan DEA) | 7 Jacki Connolly (Ballyarnett DEA) |
| 8 Brian Tierney (SDLP) | 8 Claire Russell (Sperrin DEA) | 8 Christopher Jackson (SF) |
| 9 Aisling Hutton (SF) | 9 Darren Guy (UUP) | 9 Martin Reilly (SDLP) |
| 10 Chelsea Cooke (DUP) | 10 Ruairi McHugh (SF) | 10 Paul Gallagher (IND) |
| 11 Patricia Logue (SF) | 11 Declan Norris (SDLP) | 11 Grace Uí Niallais (SF) |
|  | 12 Brian Harte (SF) |  |

| Free Choice | Statutory Partners | Social Partners (Open Call) | LCGP Partners | Elected Representatives |
| --- | --- | --- | --- | --- |

Appendix D: PEACE Plus Live Standing Conflict of Interest Declarations

| Community Regen & Transform. (CRT) |  | Thriving and Peaceful Communities Theme (TPC) |  | Celebrating Cultural Diversity Theme (CCD) |  |
| --- | --- | --- | --- | --- | --- |
| Project Title | C.O.I Declaration | Project Title | C.O.I Declaration | Project Title | C.O.I Declaration |
| Intercultural Café | Lillian Seenoi Barr | Dare 2 Dream | Alison Wallace, Sharon Doherty, Darren Guy Chelsea Cooke | The Freedom Project | Seamus Ward, Cllr Aisling Hutton |
| Green Clubs | Aódhan Harkin | Inspire, Enthuse, Equip |  | Operation Desperation |  |
| Unlock. Silent Herit. |  | Gateways to Rural Participation | Derek Moore, Kyle Thompson | HumanKind |  |
| War and Peace | Gerard Deane | Pre-teen transition Programme |  | Columba Journey |  |
| Skeoge United | Jacki Connolly | Empowered Communities Strabane | Aódhan Harkin | Culture Now Showcase | Derek Moore |
| A Stitch in Time | Lisa Moore-Maguire | Create: Youth Digital & Music Project. |  | Culmore Connections |  |
| Urban Social Farm | Charles Lamberton, | Creating Creatives |  | Out and About (BAME) | Nikki Yau |
| Waterside Together | A.Wallace, S.Doherty, C.Cooke | Strabane Youth Programme | Dominic Bonner, Aódhan Harkin | Connect (BAME) |  |
| Food Poverty Project | Sue Divin | Our Place, Our Planet |  | Let's Talk (Youth) | Anne McTaggart |
| Park Community Hall |  | Cricket Connects | Derek Moore, Kyle Thompson | Muintearas |  |
| Our Space, Our Place | Martin Duffy | IDEA |  | Our Journey to Peace | Kyra Reynolds, Derek Moore Kyle Thompson |
| Derg Future Festivals | Martin Duffy | F.Y.I. Foyleside Youth Initiative | Lisa Moore-Maguire | Fit for Purpose |  |
| Street Art Reimaging | Kyra Reynolds, Charles Lamberton | Be Wild |  | Our Present Past | Gerard Deane, Kyra Reynolds, Derek Moore, Kyle Thompson |
|  |  | Farming & Environmental Champions | Noelle Donnell | Forward Thinking | Gerard Deane |
|  |  | Sperrin Youth Voices |  | Distance Travelled |  |
|  |  | Rural Teens |  | Our Shared History |  |
|  |  | Ballyarnett Women's Programme |  | The Exodus Project | K.Reynolds, D. Guy, D. Moore |
|  |  | Be Driven | Claire Russell | Cecil Frances Alexander Celeb. | Aódhan Harkin |
|  |  | Arts & Collaborative Resilience |  | LGBTQIA+ Awareness |  |
|  |  | Ballyarnett Early Year’s Project | Jacki Connolly | Victims/Survivors Social Prog. | Aódhan Harkin |
|  |  | Ballyarnett Men's Programme |  | Culture Club | Martin Duffy |
|  |  | Reimage-Recycle |  |  |  |
|  |  | Centre of Hope | Martin Duffy |  |  |
|  |  | Art: Recovery to Discovery | Alex Duffy |  |  |