## Sheet1
Safety Advisory Group (S.A.G.) Risk Rating Category
The Safety Advisory Group initially assesses the event with the information contained within the PE1 form. It is imperative that accurate information is disclosed to enable an initial assesment to take place.
The assessment will be given a rating of green, amber, red or red+. This will help the S.A.G. to determine the scale of the events whilst reveiwing the proposed management and control measures in proportion to the scale and nature of the event. The assessment will also determine if the organisers will be recommended to attend a S.A.G. meeting.
RATINGS and Key Submission Times | Event example
GREEN PE1 Form & the 'Event Safety Managment Plan' on how the event will be managed and controlled to be sent to SAG at least 1 calendar month in advance of the event date should be submitted with PE1 form. | A green event would be deemed a low level risk with very low profile activities taking place. An example would be a sponsored walk or run of a small group of people through a park and with no impact on roads, traffic, businesses or neighbourhood.
AMBER PE1 Form should be submitted 3 calendar months before the event date. The first versionof the 'Event Safety and Management Plan' should be forward to SAG within 2 weeks of submitting the PE1 form. The final version 'Event Safety Management Plan' should be agreed 3 weeks before the event date. | An amber event is an event that has reasonable level risks associated with the event. It could be a small fireworks display, a 5k run where the route may impact on traffic and neighbourhood or an event being held in a public space within a city centre location with an expected audience/ site build that would use up more than 30% of that space.
RED PE 1 Form should be submitted 6 calendar months before the event date. The first version of the 'Event Safety and Management Plan' should be forward to SAG within 2 weeks of submitting the PE1 form. The final version 'Event Safety Management Plan' should be agreed 1 Calendar month before the event date. | A Red event is an event that has major level risks associated with the event. It could be a mass gathering of people within a confined area, a free public festival and carnival event that attracts mass gatherings and visitors from outside the city, a marathon or half marathon run where the route will impact on traffic and neighbourhood or an event being held in a public space within a city centre location with an expected audience/ site build that would use up more than 70% of that space.
RED + PE 1 Form should be submitted 8 calendar months before the event date. The first version of the 'Event Safety and Management Plan' should be forward to SAG within 3 weeks of submitting the PE1 form. The final version of the 'Event Safety Management Plan' should be agreed 4 weeks before the event date. | A Red + event is an event that is organised by multiple companies/partners attracting international artists and lasting over several days, has major level risks associated with the event. It could be a mass gathering of people within a confined area (BBC One Big Weekend/MTV) a free public festival and carnival event (Fleadh Cheoil na hEireann) that attracts mass gatherings and visitors from outside the city resulting in pop up bars and accommodation sites. An event that will impact on city centre businesses, everyday operations causing major disuption to deliveries and customer access.
Please Note:- The above is a guide to help assist potential Event Organisers. If you are planning an event and you are not sure which rating it would best fit, please contact the Safety Advisory Group's co-ordinator at Council and they will endeavour to assist you.

## Sheet2
8
9 | 88.8889